## Slide 1: Agile Planning: Step-by-Step Guide
Release Planning

## Slide 2: Release Planning: Why
where we are in the development effort,
when we will finish,
what features we will get,
what the cost will be.

## Slide 3: Release Planning: When
Timing
  a frequent, every-sprint activity.

## Slide 4: Release Planning: Who

## Slide 5: Release Planning: Overview

## Slide 6: Release Planning: Steps

## Slide 7: Release Planning (Longer-Term Planning)
every sprint, every few sprints, or continuously deployment we need longer-term, higher-level planning.
Synonyms are
  Release planning
  Longer-term planning
  Milestone-driven planning

## Slide 8: Release Planning: Time + Participant

## Slide 9: Release Planning – Process…
The inputs
  outputs of product planning
    the product vision,
    high-level product backlog,
    and product roadmap.
  velocity of the team
Activities
  Confirm the release constraints of scope, date, and budget
  Product backlog grooming, creating, estimating, and prioritizing more detailed PBIs from high-level product backlog items.

## Slide 10: Release Planning – Process…
Each release should have a well-defined set of minimum releasable features (MRFs).
produce a sprint map,
  in which sprint some or many of PBIs might be created.
The outputs of release planning are collectively referred to as the release plan.
  where we are in the development effort,
  when we will finish,
  what features we will get,
  what the cost will be.

## Slide 11: Fixed-Date Release Planning

## Slide 12: Fixed-Date Release Planning Steps

## Slide 13: Product Backlog Size vs. Team Capacity
Team Capacity:
Average faster velocity * number of Sprint = 132 Points
Average slower velocity * number of Sprint = 108 Points

## Slide 14: Must-have Size vs. Team Capacity

## Slide 15: Fixed-Scope Release Planning

## Slide 16: Fixed-Scope Release Planning Steps

## Slide 17: Fixed-Scope Planning Result
Notice that once again we give a range answer to the question we are being asked.
The question is:
“How many sprints will you need to complete a release with 150 points of work?”
The answer will be 7 to 9 sprints.
Because of two-week sprints, the answer also could be stated as 14 to 18 weeks.

## Slide 18: Release Planning Communicating

## Slide 19: Fixed-Scope Burndown Chart…

## Slide 20: References
Kenneth S. Rubin, Essential Scrum: A Practical Guide to the Most Popular Agile Process, 2012, Addison-Wesley